## Backlog & Tasks
ID | Item | Type | Status | Severity | Details | Where | Next action / owner
C1 | OCR + extraction run synchronously inside the upload request | Backlog | Open | Medium | Upload response blocks on OCR plus up to 2 sequential LLM calls. Fine at pilot volume; needs a queue/background job before multi-page or higher volume. | apps/api/src/routes/documents.ts (runOcr/runExtraction) | Decide when to introduce a job queue - Team
C2 | AWS Textract adapter is single-page only | Backlog | Open | Medium | DetectDocumentText supports single-page PDF/JPEG/PNG/TIFF. Multi-page needs async StartDocumentTextDetection + S3. | apps/api/src/services/ocr/awsTextract.ts | Weigh against Azure (multi-page native) when choosing default provider - Team
C3 | Extraction output persisted as FACT rows | Missing task | Resolved | - | persistExtractedFacts: marker resolution, forced extraction_uncertain on unmapped marker, source fields passed through, verification_state hardcoded unverified, audit rows. | apps/api/src/services/facts.ts | Done (commit ff4fe92)
C4 | Undated candidates were silently dropped | Backlog | Resolved | Medium | Now persisted with as_of_date NULL and facts.needs_manual_date=true; never dropped or given a fabricated date. documents.needs_manual_date kept as derived summary. | facts.ts; migration 003 | Done 2026-09-24 (uncommitted)
C5 | Fact inserts had no transaction | Backlog | Resolved | Medium | All inserts + audit rows + document flag for one document now in one sql.begin transaction; rollback test added. | facts.ts | Done 2026-09-24 (uncommitted)
C6 | Promise.all discarded successful field-type calls | Backlog | Resolved | Medium | Now allSettled; failed calls logged and skipped; throws only if every call failed. | anthropicExtraction.ts | Done 2026-09-24 (uncommitted)
C6-r | Partial field-type failure still ends as extraction_status='done' | Backlog | Decision needed | Medium | One field type can fail while others succeed; result is 'done' with silent gaps (console.error only). | anthropicExtraction.ts / documents.ts | Decide: add a 'partial' status or accept - Product owner
C7 | Extraction failures swallowed into console.error | Backlog | Resolved | Medium | documents.extraction_status enum (pending/done/failed) set after every run; runExtraction exported with injectable provider. | documents.ts; migration 003 | Done 2026-09-24 (uncommitted)
C7-r | No stored failure reason and no retry for failed extraction | Missing task | Open | Low | Failure reason lives only in logs; no extraction_error column; no retry action. | documents table | Design retry + optional extraction_error column - Team
C8 | Controlled marker list is a placeholder | Backlog | Open | Low (product) | CONTROLLED_MARKERS = CEA, CA-125, CA 19-9, PSA seeded illustratively; never locked by an oncologist. | packages/shared/src/markers.ts | Oncologist to approve real list - see Pending on You
T1 | Extraction Review (staff) screen | Missing task | Planned | High | Not built. Agreed design: GET /documents/:id/facts, PATCH /facts/:id (value, tracked_marker_id, as_of_date), per-fact date entry, marker mapping, extraction_status messaging. Blueprint M2 checklist item still unchecked. | apps/web/src/screens/ExtractionReview.tsx (does not exist) | Approve design, then write plan - Owner
T2 | Test against real/realistic scanned or photographed paper | Missing task | Open | High | Blueprint M2 item still unchecked. Only clean synthetic single-page PDFs exist; no noisy scans. | docs/02-implementation-blueprint.md M2 | Provide de-identified scans or add degraded-image samples - Owner
T3 | Run ingestion eval for OCR provider comparison | Missing task | Blocked | High | Scripts built and verified to fail cleanly at provider setup. .env lacks OCR_PROVIDER, EXTRACTION_PROVIDER, AWS_TEXTRACT_* vars. Azure not being evaluated (no credentials). | apps/api/src/scripts/; bun run eval:ingestion | Add credentials to .env, then run - Owner
T4 | Choose default OCR provider | Missing task | Blocked | Medium | Deliberately deferred until eval comparison exists. Only AWS currently viable for eval, so comparison is not yet possible. | - | After T3 (and Azure credentials) - Owner
T5 | Sign-off (M3) and Delta/Conflict (M4/M7) must handle NULL as_of_date | Missing task | Open | Medium | DB now blocks sign-off of undated facts (no_signoff_while_undated). Sign-off UI must surface this; delta and conflict logic (Blueprint M7 'overlapping/ambiguous as_of_date') must not assume a date. | M3/M4/M7 | Carry into M3 planning - Team
T6 | PDF-only eval samples; no image samples | Backlog | Open | Low | generateSampleDocs.ts produces 9 clean single-page PDFs only (agreed 'clean PDFs only' first pass). | apps/api/src/scripts/generateSampleDocs.ts | Extend with degraded JPEGs if wanted - Team
T7 | Migrations applied by hand; no runner | Backlog | Open | Low | schema.sql + 001 mounted by compose; 002/003 applied manually to existing DBs. No migration tool or version table. | infra/docker-compose.yml; apps/api/src/db/migrations | Decide on a migration runner before pilot - Team
T8 | Dependency check | Backlog | Open | Low | bun audit: no vulnerabilities. Only outdated item: typescript peer dep 5.9.3 -> 7.0.2 (major jump, not urgent). | package.json | Decide whether to bump - Owner
T9 | Stale OCR_API_KEY in .env | Backlog | Open | Low | Variable name is not read by providerFactory.ts (leftover). | /.env | Remove or ignore - Owner
T10 | Uncommitted work | Missing task | Open | Medium | Nothing from 2026-09-23/24 is committed: C4-C7 code, migration 003, tests, eval scripts, docs, deleted root files. | git working tree | Review and commit - Owner

## Decisions vs Docs
# | Area | What the docs say | What we did / decided | Why | Docs updated? | Impact / follow-up
1 | facts.as_of_date | Blueprint DDL and schema.sql: as_of_date DATE NOT NULL. | Nullable. Undated candidates persist with NULL date + facts.needs_manual_date=true. | Never drop data and never fabricate a date (user-directed, replaces the earlier hold-the-whole-document rule). | Blueprint DDL yes (final-state); schema.sql intentionally no (base layer); migration 003 added | Sign-off, delta, conflict logic must tolerate NULL (T5). Invariants snapshot contract already allows 'date ¦ null'.
2 | no_signoff_while_undated | Not in any doc (user referred to it as part of an 'updated Blueprint DDL' that did not exist in the repo). | Authored: CHECK (verification_state != 'oncologist_signed_off' OR as_of_date IS NOT NULL). | Oncologist attests to the as-of date; undated facts can be corrected but never signed off. | Blueprint DDL + migration 003 | Inferred from the constraint name; confirm this matches intent.
3 | documents.extraction_status | Not in Blueprint DDL. | New enum pending/done/failed. Stays pending if OCR failed or the row predates the column. | Distinguish 'extraction failed' from 'nothing extractable' (C7). | Blueprint DDL + migration 003 | Partial failures still report done (C6-r).
4 | documents.needs_manual_date and facts.raw_marker_label | Not in Blueprint DDL (added in migration 002). | documents.needs_manual_date now a derived summary; raw_marker_label holds unmapped marker text. | Support review flow for unmapped markers / undated facts. | Blueprint DDL synced 2026-09-24 | -
5 | Schema layering | Blueprint presents a single DDL. | schema.sql is the base layer; migrations 001-003 applied on top (compose init mounts, or by hand on existing DBs). | Keeps init scripts consistent; editing schema.sql would break migrations on fresh DBs. | Backlog doc note; Blueprint shows final state | Blueprint and schema.sql differ by design - potential confusion (T7).
6 | Adapter file layout | Blueprint M2: services/ocr.ts, services/extraction.ts. | Adapters live in services/ocr/{awsTextract,azureDocIntelligence}.ts and services/extraction/anthropicExtraction.ts behind services/providerFactory.ts. | Two swappable OCR vendors + provider factory. | No | Blueprint paths are stale.
7 | Marker matching | Docs describe matching against the controlled marker list. | Two steps: LLM normalizes to the controlled list; facts.ts then matches exactly (case/space-insensitive) against the patient's own tracked_markers, because tracked_marker_id is a real FK. No match -> null id, raw_marker_label set, coverage_status forced to extraction_uncertain. | FK integrity; staff always sees a mapping decision (user-specified). | Backlog doc | Unmapped markers surface only in the (unbuilt) review screen.
8 | Audit logging scope | Blueprint M3: audit on correct/sign-off/reopen. | Audit rows already written in M2: one for document upload, one per created fact (action='upload'). | User-specified; document-upload row tested 2026-09-23. | Backlog doc | -
9 | Fact persistence atomicity | No transaction requirement stated. | All facts + audit rows + document flag per document in one transaction; failure rolls back and marks extraction_status failed. | Avoid partial, undetectable fact sets (C5). | Backlog doc | -
10 | Extraction failure semantics | Not specified. | allSettled per field type; skip failed calls; throw only if all fail. | Keep useful data when one LLM call flakes (C6) without hiding total outages. | Backlog doc | Residual: partial failure = 'done' (C6-r).
11 | Upload API response shape | Not specified. | documents.ts uses RETURNING */SELECT * so every path returns needs_manual_date and extraction_status. | Removed 3x duplicated column lists (code-review finding). | Backlog doc | Clients see two new fields on every path.
12 | Extraction Review screen scope | Blueprint M2: show raw extracted text next to the structured fact for low-confidence cases. | Planned scope is larger: marker mapping, value correction, per-fact date entry, extraction_status messaging; PATCH /facts/:id also accepts tracked_marker_id and as_of_date. | Design brainstormed with user 2026-09-23, revised 2026-09-24. Earlier pending_extraction_candidates / resubmit-date design withdrawn. | Backlog doc (design section) | Blueprint checklist text not updated; screen not built (T1).
13 | Sample document set | Spec: reuse 'earlier 10-patient de-identified set if still available'. | No such set exists in the repo. Generated 9 synthetic single-page PDFs (gitignored) with pdf-lib. | Synthetic-only until DPA is confirmed; Textract is single-page only. | Backlog doc | Does not satisfy the 'realistic scanned paper' M2 item (T2).
14 | Eval tooling location | Repo scaffold lists no scripts. | apps/api/src/scripts/ with root package.json scripts eval:generate-samples and eval:ingestion; must run from repo root. | Bun loads .env from cwd only, not parent directories. | README + backlog doc | -
15 | OCR provider default | Spec: evaluate 2-3 vendors before committing. | Deferred by user until a comparison exists; only AWS Textract has a free-tier path being pursued. | User instruction: do not pick a default yet. | Backlog + third-party doc | Comparison incomplete without Azure (T3/T4).
16 | DPA scope | Spec: DPA required with the LLM vendor before real patient data. | Also flagged: OCR vendors (Azure/AWS) have no tracked DPA status. | Real documents also transit OCR vendors. | docs/third-party-services.md (new) | Confirm whether standard agreements cover this.
17 | Third-party inventory | No such document. | New docs/third-party-services.md (Postgres, Azure DI, AWS Textract, Anthropic API, local storage) with env vars, free tier, DPA status. | Requested 2026-09-23. | Created | Keep updated when providers change.
18 | README | Bun-init boilerplate. | Rewritten: setup, run, test, eval, docs index. | Docs management pass. | Yes | -
19 | Repo root cleanup | Two copies of the MVP spec and an unrelated QR PNG sat untracked at root. | Deleted (user-approved). Canonical spec remains docs/01-mvp-specification (1).md. | Duplicates; one byte-identical, one differing by one line of markdown emphasis. | - | Untracked, so not recoverable from git.
20 | Bun SQL jsonb behavior | - | Bun's built-in SQL returns jsonb columns as raw strings; JSON.parse required when asserting on audit_log.after_value. | Discovered while writing the audit test. | Backlog doc | Applies to any code reading jsonb columns.
21 | Dependencies | - | Added pdf-lib as an apps/api devDependency (sample PDF generation). bun audit clean. | Needed for synthetic samples; approved by user. | Third-party doc / README | -
22 | Docker dev DB | - | opd_postgres container had stopped; restarted with docker start. Migration 003 applied manually. | Tests could not connect otherwise. | Backlog doc | -

## Pending on You
# | Action | Why it matters | Blocks | Priority | Status
1 | Add OCR_PROVIDER=aws_textract, AWS_TEXTRACT_REGION / _ACCESS_KEY_ID / _SECRET_ACCESS_KEY and EXTRACTION_PROVIDER=anthropic to .env | Eval scripts and provider selection are ready but cannot run without them. | T3, T4 | High | Open
2 | Confirm a Data Processing Agreement with Anthropic (and decide whether Azure/AWS need one) | Spec: must close before any real patient data enters the pipeline. Synthetic data is unaffected. | Real-data testing, pilot launch | High | Open
3 | Approve or revise the Extraction Review screen design (see Backlog doc, design section) | Design is captured but nothing is built; a plan can't be written until approved. | T1 | High | Open
4 | Provide de-identified scanned/photographed samples (or approve adding degraded-image samples) | Blueprint M2 requires realistic scanned paper; current samples are clean PDFs. | T2 | High | Open
5 | Get the oncologist to approve the real controlled marker list | Placeholder list drives every 'confident match'. | C8 | Medium | Open
6 | Decide: add a 'partial' extraction_status? store a failure reason? build a retry? | Partial failures currently look successful. | C6-r, C7-r | Medium | Open
7 | Confirm no_signoff_while_undated matches your intent | I inferred the definition from its name; the Blueprint never contained it. | M3 sign-off | Medium | Open
8 | Review and commit the uncommitted work | C4-C7 code, migration 003, tests, eval scripts, docs and deletions are all uncommitted. | - | Medium | Open
9 | Apply migration 003 to any other database you use (staging/teammate DBs) | Applied only to the local opd_postgres container; no migration runner exists. | Tests/app on other DBs | Medium | Open
10 | Decide on a migration runner | Hand-applied migrations will drift. | T7 | Low | Open
11 | Decide whether to bump typescript 5.9.3 -> 7.0.2 | Only outdated dependency; major jump. | - | Low | Open
12 | Remove stale OCR_API_KEY from .env | Not read by any code. | - | Low | Open
13 | Choose the next phase (see next message) | M2 is not fully complete: review screen and real-paper testing remain. | - | Medium | Open